## Product Backlog
Planned Sprint | Actual Sprint | US ID | User Story Description | MOSCOW | Dependency | Assignee | Status
S1 | S1 | US-001 | Project Setup: Docker Compose with all 15 services (Kafka, Airflow, Spark, MinIO, PostgreSQL, Dashboard) | MUST HAVE | Docker Desktop | Varsha Sri M | 3- Completed
S1 | S1 | US-001 | PostgreSQL Schema Design: Create 7 tables — crypto_table, ohlcv_1min, top_5_gainers, top_5_losers, price_alerts, pipeline_metrics, dead_letter_queue | MUST HAVE | No Dependency | Varsha Sri M | 3- Completed
S1 | S1 | US-001 | Kafka Setup: Create crypto-prices topic with Zookeeper | MUST HAVE | No Dependency | Varsha Sri M | 3- Completed
S2 | S2 | US-001 | Airflow Producer DAG: Fetch 18 coin prices from CoinGecko API every 1 minute with data validation | MUST HAVE | CoinGecko API Key | Varsha Sri M | 3- Completed
S2 | S2 | US-001 | Airflow Producer DAG: Push validated prices to Kafka with dead letter queue for failed records | MUST HAVE | US-004 | Varsha Sri M | 3- Completed
S2 | S2 | US-001 | Airflow Producer DAG: Kafka health check, delivery verification, pipeline metrics logging to PostgreSQL | MUST HAVE | US-005 | Varsha Sri M | 3- Completed
S3 | S3 | US-001 | Spark Streaming Job: Read from Kafka, parse JSON, flatten coin data, write Parquet files to MinIO every 30 seconds | MUST HAVE | MinIO bucket setup | Varsha Sri M | 3- Completed
S3 | S3 | US-001 | MinIO Setup: Create crypto-data bucket, configure S3-compatible access for Spark | MUST HAVE | No Dependency | Varsha Sri M | 3- Completed
S4 | S4 | US-001 | Spark Analytics Job: Read Parquet from MinIO, calculate SMA, EMA, volatility, 1-min and 5-min price changes per coin | MUST HAVE | US-007 | Varsha Sri M | 3- Completed
S4 | S4 | US-001 | Spark Analytics Job: Generate OHLCV 1-minute candles, top 5 gainers, top 5 losers, price alerts on moves greater than 2% | MUST HAVE | US-009 | Varsha Sri M | 3- Completed
S4 | S4 | US-001 | Spark Analytics Job: Write all results to PostgreSQL with upsert logic and 7-day data retention cleanup | MUST HAVE | US-010 | Varsha Sri M | 3- Completed
S5 | S5 | US-001 | Airflow Analytics DAG: Trigger Spark analytics job every 5 minutes via trigger file mechanism | MUST HAVE | US-009 | Varsha Sri M | 3- Completed
S5 | S5 | US-001 | FastAPI Backend: Build 9 REST endpoints — /api/coins/latest, /api/gainers, /api/losers, /api/alerts, /api/pipeline, /api/stats, /api/health, /api/anomalies, /api/coins/{id}/summary | MUST HAVE | US-011 | Varsha Sri M | 3- Completed
S6 | S6 | US-001 | React Dashboard: Live Ticker Board showing 18 coins with 1-min and 5-min price changes | MUST HAVE | US-013 | Varsha Sri M | 3- Completed
S6 | S6 | US-001 | React Dashboard: Interactive SMA/EMA price chart, Top Movers section, Price Alerts feed, Pipeline Health status | MUST HAVE | US-014 | Varsha Sri M | 3- Completed
S7 | S7 | US-001 | React Dashboard: Fear and Greed Index gauge from Alternative.me API | SHOULD HAVE | No Dependency | Varsha Sri M | 3- Completed
S7 | S7 | US-001 | React Dashboard: Portfolio Tracker — enter coin holdings, see real-time total value, persisted in localStorage | SHOULD HAVE | US-014 | Varsha Sri M | 3- Completed
S8 | S8 | US-001 | Email Alerting: Configure SMTP for Airflow email on DAG failure, retry, and price alert triggers | SHOULD HAVE | Gmail SMTP | Varsha Sri M | 3- Completed
S8 | S8 | US-001 | SLA Monitoring: Add SLA tracking to all Airflow tasks with miss callbacks and pipeline metrics dashboard | COULD HAVE | US-006 | Varsha Sri M | 3- Completed
S8 | S8 | US-001 | Documentation: README with architecture diagram, setup instructions, API docs, troubleshooting guide | SHOULD HAVE | No Dependency | Varsha Sri M | 3- Completed

## Sprint Backlog
NOTES: Task sizing should be between 0.5 to 12 hours
US ID | Task ID | Task Description | Task Start Date | Task Completion Date | Team Member | Activity | Status | Original Estimate Effort (In Hours) | Day 1 | Day 2 | Day 3 | Day 4 | Day 5 | Day 6 | Day 7 | Day 8 | Day 9 | Day 10 | Day 11 | Day 12 | Day 13 | Day 14
[8 empty] | 104 | 41 | 38 | 25 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
SPRINT 1 BACKLOG
US-001 | 1 | Install Docker Desktop and configure docker-compose.yml with all 15 services | 2026-03-18 | 2026-03-19 | Varsha Sri M | Others | 3- Completed | 4 | Day 1: 2; Day 2: 2; Day 3: 0; Day 4: 0; Day 5: 0; Day 6: 0; Day 7: 0
US-002 | 2 | Design PostgreSQL schema with 7 tables, indexes and init.sql | 2026-03-19 | 2026-03-20 | Varsha Sri M | Design | 3- Completed | 3 | Day 1: 1; Day 2: 2; Day 3: 0; Day 4: 0; Day 5: 0; Day 6: 0; Day 7: 0
US-003 | 3 | Create Kafka crypto-prices topic and verify Zookeeper health check | 2026-03-20 | 2026-03-20 | Varsha Sri M | Others | 3- Completed | 2 | Day 1: 1; Day 2: 1; Day 3: 0; Day 4: 0; Day 5: 0; Day 6: 0; Day 7: 0
SPRINT 2 BACKLOG
US-004 | 2000-01-04 | Build Airflow Producer DAG — CoinGecko API fetch, data validation, quality checks | 2026-03-21 | 2026-03-22 | Varsha Sri M | Coding | 3- Completed | 8 | Day 1: 3; Day 2: 3; Day 3: 2; Day 4: 0; Day 5: 0; Day 6: 0; Day 7: 0
US-005 | 2000-01-05 | Add Kafka push logic with retries, error handling and dead letter queue | 2026-03-22 | 2026-03-23 | Varsha Sri M | Coding | 3- Completed | 6 | Day 1: 2; Day 2: 2; Day 3: 2; Day 4: 0; Day 5: 0; Day 6: 0; Day 7: 0
US-006 | 2000-01-06 | Add Kafka health check, delivery verification and pipeline metrics logging | 2026-03-23 | 2026-03-24 | Varsha Sri M | Coding | 3- Completed | 5 | Day 1: 2; Day 2: 1; Day 3: 2; Day 4: 0; Day 5: 0; Day 6: 0; Day 7: 0
SPRINT 3 BACKLOG
US-007 | 2000-01-07 | Build Spark Streaming job — read Kafka, parse JSON, write Parquet to MinIO | 2026-03-25 | 2026-03-26 | Varsha Sri M | Coding | 3- Completed | 10 | Day 1: 4; Day 2: 4; Day 3: 2; Day 4: 0; Day 5: 0; Day 6: 0; Day 7: 0
US-008 | 2000-01-08 | Set up MinIO crypto-data bucket and configure S3A access keys | 2026-03-25 | 2026-03-25 | Varsha Sri M | Others | 3- Completed | 2 | Day 1: 1; Day 2: 1; Day 3: 0; Day 4: 0; Day 5: 0; Day 6: 0; Day 7: 0
SPRINT 4 BACKLOG
US-009 | 2000-01-09 | Spark Analytics — calculate SMA, EMA, volatility, 1-min and 5-min price changes | 2026-03-27 | 2026-03-28 | Varsha Sri M | Coding | 3- Completed | 10 | Day 1: 4; Day 2: 3; Day 3: 3; Day 4: 0; Day 5: 0; Day 6: 0; Day 7: 0
US-010 | 2000-01-10 | Spark Analytics — OHLCV candles, top 5 gainers, top 5 losers, price alerts | 2026-03-28 | 2026-03-29 | Varsha Sri M | Coding | 3- Completed | 8 | Day 1: 3; Day 2: 3; Day 3: 2; Day 4: 0; Day 5: 0; Day 6: 0; Day 7: 0
US-011 | 2000-01-11 | Write results to PostgreSQL with upsert logic and 7-day retention cleanup | 2026-03-29 | 2026-03-29 | Varsha Sri M | Coding | 3- Completed | 5 | Day 1: 2; Day 2: 2; Day 3: 1; Day 4: 0; Day 5: 0; Day 6: 0; Day 7: 0
SPRINT 5 BACKLOG
US-012 | 2000-01-12 | Build Airflow Analytics DAG with trigger file mechanism every 5 minutes | 2026-03-30 | 2026-03-30 | Varsha Sri M | Coding | 3- Completed | 3 | Day 1: 1; Day 2: 1; Day 3: 1; Day 4: 0; Day 5: 0; Day 6: 0; Day 7: 0
US-013 | 2000-01-13 | Build FastAPI backend with 9 REST API endpoints and Swagger docs | 2026-03-30 | 2026-03-31 | Varsha Sri M | Build | 3- Completed | 8 | Day 1: 3; Day 2: 3; Day 3: 2; Day 4: 0; Day 5: 0; Day 6: 0; Day 7: 0
SPRINT 6 BACKLOG
US-014 | 14 | Build React Live Ticker Board with 18 coins and price change indicators | 2026-04-01 | 2026-04-01 | Varsha Sri M | Build | 3- Completed | 6 | Day 1: 2; Day 2: 2; Day 3: 2; Day 4: 0; Day 5: 0; Day 6: 0; Day 7: 0
US-015 | 15 | Add SMA/EMA chart, Top Movers, Alerts feed, Pipeline Health to dashboard | 2026-04-01 | 2026-04-02 | Varsha Sri M | Build | 3- Completed | 8 | Day 1: 3; Day 2: 3; Day 3: 2; Day 4: 0; Day 5: 0; Day 6: 0; Day 7: 0
SPRINT 7 BACKLOG
US-016 | 16 | Add Fear and Greed Index gauge component using Alternative.me free API | 2026-04-03 | 2026-04-03 | Varsha Sri M | Build | 3- Completed | 3 | Day 1: 1; Day 2: 1; Day 3: 1; Day 4: 0; Day 5: 0; Day 6: 0; Day 7: 0
US-017 | 17 | Add Portfolio Tracker with localStorage persistence and real-time value | 2026-04-03 | 2026-04-03 | Varsha Sri M | Build | 3- Completed | 4 | Day 1: 2; Day 2: 1; Day 3: 1; Day 4: 0; Day 5: 0; Day 6: 0; Day 7: 0
SPRINT 8 BACKLOG
US-018 | 18 | Configure Gmail SMTP for Airflow email alerts on failure and price triggers | 2026-04-04 | 2026-04-04 | Varsha Sri M | Others | 3- Completed | 3 | Day 1: 1; Day 2: 1; Day 3: 1; Day 4: 0; Day 5: 0; Day 6: 0; Day 7: 0
US-019 | 19 | Add SLA monitoring and miss callbacks to all Airflow tasks | 2026-04-04 | 2026-04-04 | Varsha Sri M | Others | 3- Completed | 2 | Day 1: 1; Day 2: 1; Day 3: 0; Day 4: 0; Day 5: 0; Day 6: 0; Day 7: 0
US-020 | 20 | Write README with architecture diagram, setup guide, API docs, troubleshooting | 2026-04-04 | 2026-04-04 | Varsha Sri M | Others | 3- Completed | 4 | Day 1: 2; Day 2: 1; Day 3: 1; Day 4: 0; Day 5: 0; Day 6: 0; Day 7: 0

## Stand up Meeting
Sprint | Day | Impediments | Action Taken
Sprint 1 | Day 1 | Docker Compose services not starting due to port conflicts on port 8080 | Identified port conflict with Docker Desktop. Changed Airflow webserver port to 8081 in docker-compose.yml
Sprint 1 | Day 2 | Zookeeper health check failing — Docker marking container as unhealthy | Confirmed Zookeeper was actually running fine. Kafka connected successfully despite the unhealthy status
Sprint 2 | Day 4 | Airflow webserver timing out — gunicorn worker killed due to insufficient RAM | Reduced gunicorn workers from 4 to 1. Stopped duplicate af-* Airflow containers consuming CPU
Sprint 2 | Day 5 | Kafka topic crypto-prices did not exist — check_kafka_health task failing | Manually created topic using docker exec kafka kafka-topics --create command
Sprint 3 | Day 7 | Spark Streaming JAR download taking over 2 minutes blocking the pipeline | Waited for initial Maven dependency download. Confirmed JARs are cached for all subsequent runs
Sprint 4 | Day 9 | MinIO bucket crypto-data not found — Spark analytics throwing NoSuchBucket error | Created bucket using mc mb local/crypto-data via MinIO client inside the container
Sprint 4 | Day 10 | Spark analytics trigger file not being created by Airflow DAG — job never starting | Fixed crypto_analytics_dag.py to use touch command instead of calling submit_analytics.sh directly
Sprint 5 | Day 12 | Dashboard API returning 404 on root URL — appeared as if service was down | Confirmed API was working correctly. Root has no route. Verified using /api/health and /docs endpoints
Sprint 6 | Day 14 | Data lag on dashboard showing 31 minutes — analytics not refreshing | Fixed analytics DAG trigger mechanism. Data lag reduced to 5-7 minutes after fix
Sprint 7 | Day 16 | Fear and Greed and Portfolio components showing dark background on light dashboard | Replaced dark Tailwind classes with light theme classes matching existing panel and muted styles
Sprint 8 | Day 18 | Git push rejected — remote had commits not present in local branch | Ran git pull origin main --no-rebase to sync remote changes before pushing

## Retrospection
SL # | Sprint # | Sprint start date | Sprint end date | Team member name | Start Doing | Stop Doing | Continue Doing | Action taken
1 | Sprint 1 | 2026-03-18 | 2026-03-20 | Varsha Sri M | Read docker-compose documentation before starting services | Assuming all containers start in correct order automatically | Checking docker compose ps after every configuration change | Added health checks and startup order using depends_on conditions
2 | Sprint 2 | 2026-03-21 | 2026-03-24 | Varsha Sri M | Validate Kafka connection before pushing data in DAG tasks | Triggering DAGs without verifying all dependencies are ready | Using environment variables from .env for all credentials | Added check_kafka_health as first task in the producer DAG pipeline
3 | Sprint 3 | 2026-03-25 | 2026-03-26 | Varsha Sri M | Create MinIO bucket before triggering any Spark streaming job | Starting Spark jobs without confirming storage bucket exists | Keeping Spark job logs visible in docker compose logs | Created crypto-data bucket in MinIO before triggering streaming
4 | Sprint 4 | 2026-03-27 | 2026-03-29 | Varsha Sri M | Test each Spark calculation independently before combining all | Writing all analytics functions in one block without testing each | Using PySpark window functions for time-series analytics | Verified SMA, EMA and OHLCV outputs against manual calculations
5 | Sprint 5 | 2026-03-30 | 2026-03-31 | Varsha Sri M | Use FastAPI /docs Swagger UI to test all APIs before building UI | Hardcoding database connection strings in source code | Using RealDictCursor for clean JSON responses from PostgreSQL | All 9 API endpoints tested and verified through Swagger UI
6 | Sprint 6 | 2026-04-01 | 2026-04-02 | Varsha Sri M | Reuse existing CSS class names (panel, muted) for all new components | Building new UI components without checking existing design patterns | Keeping dashboard auto-refresh at 15-second interval for freshness | Fixed theme mismatch by matching light theme classes from other components
7 | Sprint 7 | 2026-04-03 | 2026-04-03 | Varsha Sri M | Run git pull before every push to keep local and remote in sync | Committing pycache and auto-generated build files to git repo | Adding new entries to .gitignore for auto-generated artifacts | Successfully pushed Fear and Greed and Portfolio features to GitHub
8 | Sprint 8 | 2026-04-04 | 2026-04-04 | Varsha Sri M | Write README and documentation alongside development not after | Skipping inline comments for complex Spark and DAG logic | Following Agile sprint structure for organized feature delivery | Completed full project documentation including README and Agile template